## RACI
Step Id | Name | TPM | SDM | PM-T | Lead SDE | SDE | Business
1 | Requirements refinement | A | C | C | C | C | R
2 | Project Planning | A | C | C | C | C | C
3 | High Level Design | C | C | C | A | R | I
4 | Low Level Design | C | C | C | A | R | I
5 | Sprint Planning | R | A | I | C | C | I
6 | Daily Stand Ups | C | C | I | A | R | I
7 | Status Report | A | C | C | C | I | I
8 | Leadership Review | R | C | A | C | I | I