## Mercury Windows
ID | Epic | Predecessors | Effort
1 | P2P Communication System |  | 8 wks
2 | Design |  | 2 wks
3 | Implementation | 2 | 6 wks
4 | Windows UI - Home screen | 2 | 4 wks
5 | Design | 2 | 2 wks
6 | Implementation | 5 | 2 wks
7 | Windows UI - Messenger screen | 2 | 4 wks
8 | Design | 2 | 2 wks
9 | Implementation | 8 | 2 wks
10 | Windows UI - Find user screen | 2 | 4 wks
11 | Design | 2 | 2 wks
12 | Implementation | 11 | 2 wks
13 | Windows UI - Create profile screen | 2 | 4 wks
14 | Design | 2 | 2 wks
15 | Implementation | 14 | 2 wks
16 | End to End Testing | 1 - 15 | 4 wks

## Mercury Simple
ID | Project / Program | Milestone | Predecessor | Effort | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
1 | Windows | P2P Subsystem Ready |  | 8
2 | Windows | UI Ready | 1 | 16
3 | WIndows | E2E Testing Complete | 2 | 4
4 | macOS | P2P Subsystem Ready |  | 8
5 | macOS | UI Ready | 4 | 16
6 | macOS | E2E Testing Complete | 5 | 4
7 | Linux | P2P Subsystem Ready |  | 8
8 | Linux | UI Ready | 7 | 16
9 | Linux | E2E Testing Complete | 8 | 4
10 | Android | P2P Subsystem Ready |  | 8
11 | Android | UI Ready | 10 | 16
12 | Android | E2E Testing Complete | 11 | 4
13 | iOS | P2P Subsystem Ready |  | 8
14 | iOS | UI Ready | 13 | 16
15 | iOS | E2E Testing Complete | 14 | 4
16 | Mercury | Windows to macOS Integration Testing | 3,6 | 2
17 | Mercury | Windows to Anroid Integration Testing | 3,12 | 2
18 | Mercury | Windows to Linux Integration Testing | 3,9 | 2
19 | Mercury | Windows to iOS Integration Testing | 3,15 | 2
20 | Mercury | macOS to Linux Integration Testing | 6,9 | 2
21 | Mercury | macOS to Android Integration Testing | 6,12 | 2
22 | Mercury | macOS to iOS Integration Testing | 6,15 | 2
23 | Mercury | Linux to Android Integration Testing | 9,12 | 2
24 | Mercury | Linux to iOS Integration Testing | 9,15 | 2
25 | Mercury | Android to iOS Integration Testing | 12,15 | 2

## Stakeholders
Name | Alias | Department | Project | Role | Com Plan
Josh Teter | jteter | Mercury Program Management | All | TPM Lead | N/A
Arun Ardibeddi | aardibeddi | Windows Team | Windows Rollout | SDM | MBR
Danielle Wednesday | dwednesday | Windows Team | Windows Rollout | SDE Lead | StandUp
Bob Belkan | bbelkan | Windows Team | Windows Rollout | SDE | StandUp
Vicky Preston | vpreston | Desktop Devices Division | Windows Mac OS Linux | VP | QBR
Cassette Santoro | csantoro | Windows Team | Windows Rollout | TPM | MBR
Artem Danyluk | adanyluk | Linux Team | Subsystem | TPM | MBR
Greg Davidson | gdavidson | Mercury Program Management | All | PM-T Lead | N/A

## RACI
Step Id | Name | TPM | SDM | PM-T | Lead SDE | SDE | Business
1 | Requirements refinement | A | C | C | C | C | R
2 | Project Planning | A | C | C | C | C | C
3 | High Level Design | C | C | C | A | R | I
4 | Low Level Design | C | C | C | A | R | I
5 | Sprint Planning | R | A | I | C | C | I
6 | Daily Stand Ups | C | C | I | A | R | I
7 | Status Report | A | C | C | C | I | I
8 | MBR | R | C | A | C | I | I

## Tech RACI
Key Management Area | Step | Role
Planning | Refine requirements | A
| Create functional spec | A/R
| Sprint planning | R/C
| Review designs | C
Stakeholder Management | Draft communication plan | R/A
| Daily Stand Ups | C
| Status Report | A
| MBR | R
Risk Management | Risk analysis | A
| Risk monitoring | A/R
| Issue resolution | A

## Specializations
|  |  |  | AppSec | Security | GPO | SA | TPM
AppSec TPM | Networking knowledge - protocols | Network | Network | x
AppSec TPM | Security Architecture experience | Security | Security | x | x
Security TPM | App Security | Security
AppSec TPM | Experience in multiple programming languages | Code | General Tech |  |  |  |  | x
Security TPM | Risk Management Framework | PMP | Code | x
Security TPM | Incident Response | PMP
Security TPM | Security Assessment | PMP | Cloud |  |  |  | x
TPM - GPO | PMP | PMP | Systems Design |  |  |  |  | x
TPM - GPO | Change acceleration and change management | PMP
TPM - GPO | Process improvement skills | PMP | PMP |  | x | x |  | x
TPM | Project and Program Proficiency | PMP
TPM | Technical degree | General
TPM | Systems Design | Systems Design
Solutions Architect - TPM | Integration full-stack | Cloud
Solutions Architect - TPM | E2E architectural knowledge | Cloud

## Comm Plan
Plan | Goal | Recurrence | Owner | Distribution
Stand Up | Day-to-day collaboration and unblocking progress | Daily | SDE Lead | Sprint Board
Leadership Review | Leadership-level program status with key insights relevant to leadership | 3rd Monday of every month | TPM Lead | Meeting and Email
Senior Leadership Review | Senior Leadership-level program status | 3rd Monday of first month per quarter | PM-T Lead | Meeting and Email
Status Update | Milestone-level project status | Every Wednesday | Project TPM | Email

## Risk Register
ID | Project/ Program | Risk | Realized | Strategy
1 | Windows Todo App | Network testing failures | Yes | Acceptance - 3 week milestone slip
2 | Linux Todo App | Distribution regressions | No | Mitigation
3 | Android Project Tracker | App approval delays | Yes | Acceptance - 2 week addition
4 | iOS Project Tracker | App approval delays | Yes | Acceptance - 3 week addition

## Risk Log
Id | Risk | Probability | Impact | Strategy | Project Occurrence | Categories
1 | Cross-platform tooling issues | High | High | Acceptance: Shift timelines to account for delays Mitigation: training and crashing
2 | Tight testing timeline | Medium | Medium | Acceptance: Shift timelines to account for delays Mitigation: shift timelines to allow for buffer
3 | App store approval delays | Low | Low | Acceptance: Shift timelines to account for delays
Id | Risk | Probability | Impact | Strategy
1 | Cross-platform tooling issues | High | High | Acceptance: Shift timelines to account for delays Mitigation: training and crashing
1.1 | New Integrated Desktop Environment (IDE) | High | High | Mitigation: training on new IDE
1.2 | New Coding Language for some teams | High | High | Mitigation: training on new language
1.3 | Cross-team collaboration | High | Medium | Mitigation: daily stand ups, co-location or chat rooms
2 | Tight testing timeline | Medium | Medium | Acceptance: Shift timelines to account for delays Mitigation: shift timelines to allow for buffer
3 | App store approval delays | Low | Low | Acceptance: Shift timelines to account for delays

## Scorecard
Probability | Impact | Risk Score | P | I | R
Low (1) | Low (1) | Low (2) | 1 | 1 | 2 | Low
Medium (2) | Low (1) | Low (3) | 2 | 1 | 3 | Low
High (3) | Low (1) | Medium (4) | 3 | 1 | 4 | Medium
Low (1) | Medium (2) | Low (3) | 1 | 2 | 3 | Low
Medium (2) | Medium (2) | Medium (4) | 2 | 2 | 4 | Medium
High (3) | Medium (2) | Medium (5) | 3 | 2 | 5 | Medium
Low (1) | High (3) | Medium (4) | 1 | 3 | 4 | Medium
Medium (2) | High (3) | Medium (5) | 2 | 3 | 5 | Medium
High (3) | High (3) | High (6) | 3 | 3 | 6 | High

## Requirements
ID | Requirements
1 | Peer-to-peer messaging system
2 | System must allow to send text messages to other peers on the system
3 | Standard UX elements from other messaging apps should be available
4 | All messages sent and received for a user must be accessible by the user from within the app unless they explicitly delete a message
1 | A peer-to-peer messaging system, with no servers, should be created
1.1 | Company-managed relay servers can be made available via configuration but will not require the peer-to-peer installation to setup anything extra to use them
1.2 | The relay server option should be configurable to satisfy client infosec requirements
1.3 | The P2P network should be deployable to a closed network or open (with the use of relay servers)
2 | The system must allow to send text messages to other users on the network/system
2.1 | The text message should support all unicode characters, including emojis
3 | Standard UX elements seen in other messaging apps should be available
3.1 | Address Book of saved contacts
3.1.1 | Add to address book
3.1.2 | Remove from address book
3.1.3 | Load address book entirely or a single address
3.1.4 | Export address book entirely or a single address
3.2 | User Profile
3.2.1 | User profile image
3.2.2 | User alias should be changeable
3.2.3 | Short bio section including description/bio, company, title
3.3 | Presence indicator
3.3.1 | Configurable statuses
3.3.2 | Configurable locations
3.4 | Access control
3.4.1 | User should be able to accept contact request
3.4.2 | User should be able to block contact request
4 | All messages sent and received should be visible to the user
4.1 | Exception for when a message is deleted by the user
4.2 | Messages should contain a status indicator of { sent, received, read }

## Use Cases
ID | ReqIds | Use Case
1 | 1.0-1.3 | As an admin, have no centralized setup or maintenance
2 | 1.0-1.3 | As a user, install and use without a central server
3 | 3.2 | As a user, create a user profile with picture and alias
4 | 3.1 | As a user, add or remove a contact to my contact list
5 | 3.4 | As a user, block and accept a contact request
6 | 2 | As a user, send message to a contact
7 | 4 | As a user, see new messages sent to me
8 | 4 | As a user, see all messages both sent and received
9 | 3.3 | As a user, set presence information

## Tasks
ID | ReqId | Task | Duration | Dependencies
1 | 1 | Create P2P Network | 12
2 | 1 | Design Network | 4
3 | 1 | Implement | 6 | 2
4 | 1.3 | Create networkId to tie a message to a given network instance | 2 | 3
5 | 1.1 | Relay Servers | 14
6 |  | Setup Relay Servers | 10
7 |  | Design | 4
8 |  | Implement | 6 | 7
9 | 1.2 | Make Relay Configurable | 2 | 8
10 | 1.3 | Relay should have an allow/deny list to ensure closed instances remain closed | 2 | 8
11 | 2 | Text Message Send/Receive API | 8
12 | 2 | Setup API for Request/Response | 4
13 | 4.2 | Use an Ack tag to track message status | 2 | 12
14 | 2.1 | Ensure unicode support in api payload | 1 | 12
15 | 3.4.1 | New text message to new contact initiates contact request | 1 | 12
16 | 3.1 | Address Book | 16
17 | 3.1.1/2 | Add/Remove API using message protocol/API | 4
18 | 3.1.3/4 | Import/Export of AddressBook | 4 | 17
19 | 3.1.3/4 | Import/Export of AddressEntry | 4 | 17
20 |  | Support Search/Discovery for members on network | 4 | 17
21 | 3.2 | User Profile Object | 3
22 | 3.2.1 | CRUD | 1
23 | 3.2.2 | Alias CRUD | 1
24 | 3.2.3 | Bio Text CRUD | 1
25 | 3.3 | Presence Object | 2.5
26 | 3.3.1 | Status Key Value Pair | 1
27 | 3.3.2 | Location Key Value Pair | 1
28 | 3.3 | Support Full Unicode including emojis in Values | 0.5
29 | 3.4 | Access Control | 1
30 | 3.4 | Accept or Deny Contact request | 1
31 | 4 | Message Library | 2.5
32 | 4.1 | Maintain message list for both sent and received | 2 | 12
33 | 4.1 | Allow Deletion of Sent/Received message from list | 0.5 | 12

## Project Plan
[9 empty] | Actual | 2 | 2 | 2 | 3 | 3 | 2 | 2
[9 empty] | Planned | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3
ID | ReqId | Task | Duration | Swarm # | Predecessors | Resourcing | Start Date | End Date |  | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15 | 2022-05-22 | 2022-05-29 | 2022-06-05 | 2022-06-12 | 2022-06-19
1 | 1 | Create P2P Network | 16
2 | 1 | Design Network | 6 | 1 |  | Arun | 2023-01-02 | 2023-02-06 | bar: 2022-01-02 to 2022-02-06
3 | 1 | Implement | 10 | 2 | 2fs | Arun, Bex | 2023-02-13 | 2023-03-24 | bar: 2022-02-13 to 2022-03-20
4 | 1.3 | Create networkId to tie a message to a given network instance | 3 | 1 | 2fs | Arun | 2023-03-27 | 2023-04-14 | bar: 2022-03-27 to 2022-04-10
5 | 2 | Text Message Send/Receive API | 13
6 | 2 | Setup API for Request/Response | 6 | 2 |  | Danielle, Eliza | 2023-01-02 | 2023-01-20 | bar: 2022-01-02 to 2022-01-16
7 | 4.2 | Use an Ack tag to track message status | 3 | 1 | 6fs | Danielle | 2023-01-23 | 2023-02-17 | bar: 2022-01-23 to 2022-02-13
8 | 2.1 | Ensure unicode support in api payload | 2 | 1 | 6fs | Eliza | 2023-01-23 | 2023-02-03 | bar: 2022-01-23 to 2022-01-30
9 | 3.4.1 | New text message to new contact initiates contact request | 2 | 1 | 6fs | Eliza | 2023-02-06 | 2023-02-17 | bar: 2022-02-06 to 2022-02-13
10 | 3.1 | Address Book | 20
11 | 3.1.1/2 | Add/Remove API using message protocol/API | 6 | 2 |  | Arun, Bex | 2023-04-17 | 2023-05-05 | bar: 2022-04-17 to 2022-05-01
12 | 3.1.3/4 | Import/Export of AddressBook | 5 | 1 | 11fs | Arun | 2023-05-08 | 2023-06-09 | bar: 2022-05-08 to 2022-06-05
13 | 3.1.3/4 | Import/Export of AddressEntry | 5 | 1 | 11fs | Bex | 2023-05-08 | 2023-06-09 | bar: 2022-05-08 to 2022-06-05
14 |  | Support Search/Discovery for members on network | 5 | 1 | 11fs | Charley | 2023-05-08 | 2023-06-09 | bar: 2022-05-08 to 2022-06-05
15 | 3.2 | User Profile Object | 3
16 | 3.2.1 | CRUD | 1 | 1 |  | Danielle | 2023-02-20 | 2023-02-24 | bar: 2022-02-20
17 | 3.2.2 | Alias CRUD | 1 | 1 |  | Eliza | 2023-02-20 | 2023-02-24 | bar: 2022-02-20
18 | 3.2.3 | Bio Text CRUD | 1 | 1 |  | Danielle | 2023-02-27 | 2023-03-03 | bar: 2022-02-27
19 | 3.3 | Presence Object | 3
20 | 3.3.1 | Status Key Value Pair | 1 | 1 |  | Eliza | 2023-02-27 | 2023-03-03 | bar: 2022-02-27
21 | 3.3.2 | Location Key Value Pair | 1 | 1 |  | Danielle | 2023-03-06 | 2023-03-13 | bar: 2022-03-06
22 | 3.3 | Support Full Unicode including emojis in Values | 1 | 1 |  | Eliza | 2023-03-06 | 2023-03-13 | bar: 2022-03-06
23 | 3.4 | Access Control | 1
24 | 3.4 | Accept or Deny Contact request | 1 | 1 |  | Eliza | 2023-03-20 | 2023-03-24 | bar: 2022-03-13 to 2022-03-20
25 | 4 | Message Library | 3
26 | 4.1 | Maintain message list for both sent and received | 2 | 1 |  | Danielle | 2023-03-20 | 2023-04-07 | bar: 2022-03-20 to 2022-04-03
27 | 4.1 | Allow Deletion of Sent/Received message from list | 1 | 1 | 26fs | Eliza | 2023-03-27 | 2023-03-31 | bar: 2022-03-27
28 |  | On-call Rotations | bar: 2022-03-27
29 |  | Danielle On-call | 1 | 1 |  | Danielle | 2023-02-06 | 2023-02-10 | bar: 2022-02-06
31 |  | Arun On-Call | 1 | 1 |  | Arun | 2023-02-20 | 2023-02-24 | bar: 2022-02-20
32 |  | Bex On-Call | 1 | 1 |  | Bex | 2023-03-06 | 2023-03-10 | bar: 2022-03-06
33 |  | Eliza On-call | 1 | 1 |  | Eliza | 2023-03-13 | 2023-03-17 | bar: 2022-03-13
34 |  | Danielle On-call | 1 | 1 |  | Danielle | 2023-03-27 | 2023-03-31 | bar: 2022-03-27

## Burndown Chart
|  | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3
|  | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10
60 | Planned | 58 | 56 | 54 | 51 | 48 | 45 | 42 | 39 | 36 | 33 | 30 | 27 | 24 | 22 | 21 | 19 | 17 | 15 | 12 | 9 | 6 | 3 | 0
60 | Actual | 2024-09-09: 58; 2024-09-16: 56; 2024-09-23: 54; 2024-09-30: 51; 2024-10-07: 48; 2024-10-14: 46; 2024-10-21: 44

## Project Plan w Relays
ID | ReqId | Task | Duration | Swarm # | Predecessors | Resourcing | Start Date | End Date | Jan | Feb | Mar | Apr | May | June
1 | 1 | Create P2P Network | 16
2 | 1 | Design Network | 6 | 1 |  | Arun | 2023-01-02 | 2023-02-13
3 | 1 | Implement | 10 | 2 | 2fs | Arun, Bex | 2023-02-14 | 2023-03-28
4 | 1.3 | Create networkId to tie a message to a given network instance | 3 | 1 | 2fs | Arun | 2023-03-29 | 2023-04-19
5 | 1.1 | Relay Servers | 19
6 |  | Setup Relay Servers | 13
7 |  | Design | 5 | 1 | 2fs | Charley | 2023-02-20 | 2023-03-27
8 |  | Implement | 8 | 2 | 7fs | Charley,Bex | 2023-03-28 | 2023-04-25
9 | 1.2 | Make Relay Configurable | 3 | 1 | 7fs | Charley | 2023-04-26 | 2023-05-17
10 | 1.3 | Relay should have an allow/deny list to ensure closed instances remain closed | 3 | 1 | 7fs | Bex | 2023-04-26 | 2023-05-17
11 | 2 | Text Message Send/Receive API | 13
12 | 2 | Setup API for Request/Response | 6 | 2 |  | Danielle, Eliza | 2023-01-02 | 2023-01-23
13 | 4.2 | Use an Ack tag to track message status | 3 | 1 | 12fs | Danielle | 2023-01-24 | 2023-02-21
14 | 2.1 | Ensure unicode support in api payload | 2 | 1 | 12fs | Eliza | 2023-01-24 | 2023-02-07
15 | 3.4.1 | New text message to new contact initiates contact request | 2 | 1 | 12fs | Eliza | 2023-02-08 | 2023-02-22
16 | 3.1 | Address Book | 20
17 | 3.1.1/2 | Add/Remove API using message protocol/API | 6 | 2 |  | Arun | 2023-04-20 | 2023-05-11
18 | 3.1.3/4 | Import/Export of AddressBook | 5 | 1 | 17fs | Arun | 2023-05-12 | 2023-06-16
19 | 3.1.3/4 | Import/Export of AddressEntry | 5 | 1 | 17fs | Bex | 2023-05-18 | 2023-06-22
20 |  | Support Search/Discovery for members on network | 5 | 1 | 17fs | Charley | 2023-05-18 | 2023-06-22
21 | 3.2 | User Profile Object | 3
22 | 3.2.1 | CRUD | 1 | 1 |  | Danielle | 2023-02-22 | 2023-03-01
23 | 3.2.2 | Alias CRUD | 1 | 1 |  | Eliza | 2023-02-23 | 2023-03-02
24 | 3.2.3 | Bio Text CRUD | 1 | 1 |  | Danielle | 2023-03-02 | 2023-03-09
25 | 3.3 | Presence Object | 3
26 | 3.3.1 | Status Key Value Pair | 1 | 1 |  | Danielle | 2023-03-10 | 2023-03-17
27 | 3.3.2 | Location Key Value Pair | 1 | 1 |  | Eliza | 2023-03-06 | 2023-03-13
28 | 3.3 | Support Full Unicode including emojis in Values | 1 | 1 |  | Danielle | 2023-03-18 | 2023-03-25
29 | 3.4 | Access Control | 1
30 | 3.4 | Accept or Deny Contact request | 1 | 1 |  | Eliza | 2023-03-20 | 2023-03-27
31 | 4 | Message Library | 3
32 | 4.1 | Maintain message list for both sent and received | 2 | 1 |  | Danielle | 2023-04-03 | 2023-04-17
33 | 4.1 | Allow Deletion of Sent/Received message from list | 1 | 1 | 32fs | Eliza | 2023-03-27 | 2023-04-03
34 |  | Danielle On-call | 1 | 1 |  | Danielle | 2023-02-06 | 2023-02-10
35 |  | Charley On-call | 1 | 1 |  | Charley | 2023-02-13 | 2023-02-17
36 |  | Arun On-Call | 1 | 1 |  | Arun | 2023-02-20 | 2023-02-24
37 |  | Bex On-Call | 1 | 1 |  | Bex | 2023-03-06 | 2023-03-10
38 |  | Eliza On-call | 1 | 1 |  | Eliza | 2023-03-13 | 2023-03-17
39 |  | Danielle On-call | 1 | 1 |  | Danielle | 2023-03-27 | 2023-03-31
Formulas:
End Date = [Start Date]+(([Duration]*7)/[Swarm #])
Start Date = [End Date, row above]+1

## Features
Feature | Start Date | End Date
Create P2P Network
Relay Servers
Setup Relay Servers
Text Message Send/Receive API
Address Book
User Profile Object
Presence Object
Access Control
Message Library

## PM Tools
Tool | Project Management | Portfolio Management | Resource Management | Stakeholder Management | Freeform
MS Project | x |  | x | x
Smartsheet | x | x | x | x
Clarizen | x | x | x | x
Asana | x | x | x | x
MS Excel |  |  |  |  | x

## Buffer Scorecard
Level of Ambiguity in Task | Confidence of estimate accuracy | Team Overhead | Buffer
Medium | Low | 10% | 35%
High | Low | 10% | 40%
Low | Medium | 10% | 25%
Medium | Medium | 10% | 30%
High | Medium | 10% | 35%
Low | High | 10% | 20%
Medium | High | 10% | 25%
High | 15 | Low
Medium | 10 | Medium
Low | 5 | High

## Resourcing
| April | May | June | July | August | September | October | November | December
Planned | 4 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 44 | 44
Requested | 4 | 9 | 8 | 8 | 11 | 9 | 9 | 3 | 3 | 64 | 49
Actual | 4 | 9 | 8 | 7 | 8 | 8 | 6 | 3 | 3 | 56 | 44